## Events Process Document
EVENTS PROCESS DOCUMENT
INFORMATION
Process Name: | EVENTS ORGANIZATION PROCESS DOCUMENT
Process Owner: | Events Specialist
Last Date Updated: | 2026-09-03
Process Approval: | Associate Director, Marketing and Communications
Objective: | This document serves as a resource for College of Liberal Arts departments, units, and centers who want to host events.
SCOPE
This process document applies to events that require coordination and promotion outside of the individual department, unit, or center for lectures, conferences, workshops, panel discussions, or any other such event.
ROLES AND RESPONSIBILITIES
Event logistics: | Coordinate event details, timelines, vendors, equipment, and overall event operations.
Promotion: | Support event marketing through email, social media, websites, signage, and other communications.
Budget: | Track event expenses, payments, estimates, and overall budget management.
On-Site Staff Assistance: | Assist with event setup, guest support, coordination, troubleshooting, and cleanup during the event.
EVENT PROCESS
3-12 Months Prior: | Confirm goals, audience, budget
3-12 Months Prior: | Complete CLA Event Request Form: https://purdue.ca1.qualtrics.com/jfe/form/SV_4GEnA02cPaNcyZE
3 Months Prior: | Reserve venue; parking/transportation
3 Months Prior: | Confirm speakers, gather bios
9 Weeks Prior: | Marketing plan: email, website, social media
8 Weeks Prior: | Registration complete (accommodations; dietary restrictions)
8 Weeks Prior: | Order promotional items if required
6 Weeks Prior: | Invitations sent
4 Weeks Prior: | Create day of show document; include staff assignments; timeline; speaker management; registration procedures
4 Weeks Prior: | Catering finalized; onsite vendors: photography, AV, accessibility accommodations, room set up
1 Week Prior | Final walkthrough; Name badges, Attendance tracking
2 Days Prior: | Print materials, confirm room set-up, send reminders
Event Day: | Arrive early; test AV; welcome guests, capture photos, track attendance
1 Week After: | Thank-you communications; budget reconciliation; Share photos
2 Weeks After: | Post-event assessment
TEMPLATES AND RESOURCES
Process Documents: | https://www.cla.purdue.edu/resources/digital-media/files/events/events-process-info.xlsx
Vendors List (West Lafayette): | https://www.cla.purdue.edu/resources/digital-media/files/events/vendors-west-lafayette.xlsx
Vendors List (Indy): | https://www.cla.purdue.edu/resources/digital-media/files/events/vendors-indianapolis.xlsx
Run-Of-Show Document: | https://www.cla.purdue.edu/resources/digital-media/files/events/run-of-show-template.docx
EVENT CONSIDERATIONS
Venue: | Reserve Room
Verify Capacity
Confirm Accessibility
Arrange Room Setup
Budget: | Catering
Speaker expenses
Travel
Materials
Parking
Photography
Guests: | Invitations
Registration
Name badges
Special accommodations
Technology: | Projector
Microphones
Recording/streaming
Hybrid participation
Hospitality: | Catering
Dietary restrictions
VIP hosting
Marketing and Promotion: | Event calendar submission
Website event listings
Social media requests
Email promotion opportunities
Digital signage
Purdue Today
Working with Speakers and Guests: | Honoraria
Travel arrangements
Lodging
Speaker bios and headshots
Presentation materials
Thank-you notes
University Policies/Requirements: | Accessibility requirements
Contracts and agreements
Risk management
Youth protection policies
Photography permissions
Procurement requirements
Resources and Contacts: | Marketing requests
Web requests
Event calendar submission link
Photography request link
Room reservation information